## Additional Feature List
Task | Time(Days) | Statues | Start Date | End Date
Import College/Course/Company and autofill at their respective placeholder | 7 | In Production
Team Based Change in Industry Ready Competitiion | 3 | In Production | 0
Finance View | 7 | In Production | 0
Product Based Coupon Code(UI + Backend Development) | 10 | Pending | 2019-04-04 | 2019-04-13
Google Recaptcha Integeration | 7 | Pending | 2019-04-14 | 2019-04-20

## Optimization task
Task | Time(Days) | Status | Start Date | End Date
Static Files(JS, CSS, Fonts) Otimization and minification | 7 | Pending | 2019-04-21 | 2019-04-27
CDN Implmentation: 1. CDN Setup 2. Changing Upload path of images to CDN from server 3. Changing local image path to CDN path 4. Migrating existing images / static files to CDN | 15 | Pending | 2019-04-28 | 2019-05-12
Data Caching 1. Setting Up Memcache 2. Writing wrapper to fetch and store data from Memcahed 3. Maintainig cache on Static Content/ Product Content update | 15 | Pending | 2019-05-13 | 2019-05-27
DB optimization 1. Indexing DB 2. Debug and resolve slow queris 3. Minimizing DB read operation | 15 | Pending | 2019-05-28 | 2019-06-11